## Sheet2
NTINGA O.R. TAMBO DEVELOPMENT AGENCY SOC LTD
2020/2021 MIDTERM PERFORMANCE REPORT (JULY- DECEMBER 2020)
STRATEGIC GOAL 1 | Sustainable Water Services (water supply and sanitation) Systems.
Objectives | Key Performance Indicator | Project Names | Indicator Code | Interventions/ Critical Success Factors | 2017/2018 Budget | Baseline 2019/20 | 2020/21 Annual Performance Target | Quarter 1 Target (01 July- 30 September 2020) | Quarter 2 Target (01 October - 31 December 2020) | Midterm Actual Performance | Performance Variance & Reasons | Corrective Measure | Means of Verification | Custodian
1.1 Provide repair and physicalinfrastructure maintanance services to peri urban and rural village water supply schemes | 1.1.1 Number of repaired water supply schemes, revenue generated from repairs in each water supply scheme, revenue generated from maintenance in each water supply scheme | Assessment, refurbishment and maintenance of 93 water schemes | 1_1.1_2_P02 | Availability of adequate repairs and maintenance budget |  | Refurbishment of 50 water schemes. | Repairing of 22 water schemes | 5 water Schemes repaired | 5 water Schemes repaired | Achieved: 10 water schemes were repaired | Not Applicable | Not Applicable | Job Cards for repaired Water Schemes (Q1-Q4) | Head: Water Services
[7 empty] | maintenance of 93 water schemes | maintenance of 24 water schemes | maintenance of 24 water schemes (completed forms) | Achieved: 49 water schemes were maintained | Not Applicable | Not Applicable | Job Cards for Maintained Water Schemes (Q1- Q4) | Head: Water Services
1.2 Provide accurate data of households, businesses, that have yard connections and levy the approvrd tarrif each consumer category | 1.2.1 Number of households that have yard connections in each water supply scheme, number of churches and schools that have yard water connections in each water supply scheme | P04 Rural Billing data collection | 1_1.1_4_P04 | Development of cash/revenue collection system, establishment of a fully equiped repairs and maintenance workshop | Phase | Households and Businesses with yard water connections in each water supply scheme, Businesses with yard water connections in each water supply scheme, Churches and schools with yard water connections in each water supply schemes | Collecting data from 500 businesses , collecting 150 Churches and schools, collecting 1500 households | collecting 400 consumer data (completed forms) | collecting 600 consumer data (completed forms) | Partially Achieved: 1082 consumer data collected | The only outstanding matter is for the consumers to fill-in Ntinga application form. | Water consumers appearing on the datadase will be given applications forms to fill-in their details. | Consumer Data collected (Q1 - Q4) | Head: Water Services
| 1.2.2 Revenue generated by water services department from maintenance of water schemes | Revenue generation |  | Revenue generated by the business unit |  | R10,172,346.00 | R15,288,900.00 generated from water services operations | R3,822,223.00 generated from refurbishment and maintenance of water schemes | R3,822,225.00 generated from refurbishment and maintenance of water schemes | Achieved: R8 088 599 | Not Applicable | Not Applicable | * Invoices * Proof of payment | Head: Water Services
| 1.2.3 Revenue generated from billing water consumers | Consumer billing |  | Cash collection partnerships with banks, chainstores |  | Nill | R1 million collected from billing water consumers. | No target set for this period. | R333,333 collected from water consumers. | Not Achieved: No revenue collected from water consumers. | Registration of water consumers has not yet been concluded. | As soon as registration is concluded billing will commence. This will be done in phases and we will not wait to register all peri-urban areas before commencing with billing. | * Invoices * Proof of payment | CFO
STRATEGIC GOAL 2 | Enhanced and Enabled Full Value Chains (upstream and downstream) for Agricultural Produce, Markets, Abattoir and Aquaculture
Strategic Objectives | Key Performance Indicator | Project Names | Indicator Code | Interventions | 2017/2018 Budget | Baseline 2019/20 | 2020/21 Annual Performance Target | Quarter 1 (01 July 2020 - 30 Sept 2020) | Quarter 2 (01 October 2020- 31 December 2020) | Midterm Actual Perfomance | Performance Variance & Reasons | Corrective Measure | Means of Verification | Custodian
2.1 Improve productivity and profitability of Umzikantu Abattoir by 30 June 2021. | 2.1.1 Number of livestock units slaughtered for communities, butcheries and other | P09 Abattoir Private Slaughter | 2_2.1_1_P09 | - Refurbishment and continuous maintenance of abattoir infrastructure and facilities. - Production and marketing of red meat (cattle, sheep, goats & pigs) carcasses and offal, locally and beyond. - Utilisation of abattoir for slaughtering incrementally towards full capacity. |  |  | 900 Livestock units slaughtered for communities, butcheries, and others. (50% increase from the previous financial year) | 180 Livestock units slaughtered for communities, butcheries, and others. | 315 Livestock units slaughtered for communities, butcheries, and others. | Partially Achieved: 271.91 Livestock units slaughtered for communities, butcheries, and others. | A negative varience of 223.09 livestock units was observed This is due to Covid Regulations and the fact that most of the farmers are still sending animals unbranded. These figures do not include December. | This is difficult to control at this stage as there is no way to really market the availability of the abattoir to slaughter because of Covid | Batch control documents. | Head: Trading Enterprises | 378000
| 2.1.2 Number of livestock units slaughtered for sale, towards abattoir full capacity | P10 Abattoir Own Livestock Slaughter | 2_2.1_2_P10 |  |  |  | 1155 Livestock units slaughtered for sale, towards abattoir full capacity. (2.37% Decline from the previous financial year) | 231 Livestock units slaughtered for sale, towards abattoir full capacity. | 404 Livestock units slaughtered for sale, towards abattoir full capacity. | Partially Achieved: 492 Livestock units slaughtered for sale, towards abattoir full capacity. | A negative varience of 143 Livestock units was experienced . This target was set thinking that the meat market will be operational at KFPM. The abattoir also experienced water crisis during Christmas Week, which made it dificult for the abattoir to slaughter and sell. | This can only be rectified once the meat market is fuctional. | Batch control documents. | Head: Trading Enterprises | 630
| 2.1.3 Revenue generated from meat sales and slaughter fees | P11 Abattoir Meat Sales | 2_2.1_3_P11 |  |  |  | R7,367,615.00 Revenue generated from meat sales and slaughter fees. (26.77% increase from the previous financial year) | R1 473 525 Revenue generated from meat sales and slaughter fees. | R2 578 662 Revenue generated from meat sales and slaughter fees. | Over Achieved: R5 942 365.64Revenue generated from meat sales and slaughter fees. | A positive variance of R1 890 178.64 revenue was experienced. This target was set thinking that the meat market will be operational at KFPM. Part bof the revenue realised here was supposed to be realised at KFPM | This can only be rectified during the SDBIP review | Financial Reports | Head: Trading Enterprises | 94500 | 1816018
2.2 Improve functionality and viability of Kei Fresh Produce Market (KFPM) by initially focusing and targeting linkages of fruits, vegetables and meat industry supply chains by 30 June 2021. | 2.2.1 Tonnage of agricultural produce sold by Market Agents | P14 Fresh Produce Market tonnage | 2_2.2_1_P14 | - Refurbishment and continuous maintenance of Market infrastructure and facilities. - Recruitment of competent Market Agents towards full capacity of the Market. - Encourage aggressive marketing and sale of fresh produce (fruit and vegetables) locally and beyond by Market Agents. |  |  | 6 538 Tons of agricultural produce sold by Market Agents. | 654 Tons of agricultural produce sold by Market Agents. | 2 288 Tons of agricultural produce sold by Market Agents. | Not Achieved: 1 189.73 Tons of agricultural produce sold by Market Agents. | A negative variance of 1 927 tons of agricultural fresh produce sod by agents was experienced | Market Management to seek for more market agents so as to improve fresh produce supply | Freshmark System monthly reports. | Head: Trading Enterprises
| 2.2.2 Revenue generated from 5% commission of agricultural produce sold | P16 Fresh Produce Market Commission | 2_2.2_3_P16 |  |  |  | R2,045,821.05 Revenue generated from 5% commission of agricultural produce sold. | R204,582.10 Revenue generated from 5% commission of agricultural produce sold. | R818,328.42 Revenue generated from 5% commission of agricultural produce sold. | Not Achieved: R257 599.68 Revenue generated from 5% commission of agricultural produce sold. | A negative variance of R793 157.89 revenue generation from 5% commission of agricultural produce was experienced | Market Management to seek for more market agents so as to improve fresh produce supply and revenue generation. | Freshmark System monthly reports. | Head: Trading Enterprises
| 2.2.3 Full utilisation of KFPM floor space for revenue generation | P17 Fresh Produce Market Profitability | 2_2.2_4_P17 |  |  | 2 Market Agents trading at KFPM | 1 Additional competetive Market Agent secured who can feel floor space | No target set | No target set | Not target set | Still have 1 market agent out of possible 4 | In talks with a potential Market Agent who is expected to start operating at the market by February 2021. | Freshmark System monthly reports. | Head: Trading Enterprises
|  |  | 2_2.2_5_P18 | Increase in supply of meat in kilograms for sustainability of the Market |  | None | 132 382.52 Kilograms sold by the Market | No target | 19 752.13 Kilograms sold by the Market | Not achieved: | The budget is not enough to build a meat market | Head Trading Enterprises is looking for possible funding from ECRDA and DAFF | Stock Control Book. | Head: Trading Enterprises
| 2.2.4 Revenue generated from meat market sales | P18 Meat Market Revenue Generation | 2_2.2_5_P18 | Increase revenue generation for sustainabilty of the Market |  | None | R7, 876, 760.00 Revenue generated from meat market sales. | No Target | R1, 175, 252.00 Revenue generated from meat market sales. | Not achieved: | The budget is not enough to build a meat market | Head Trading Enterprises is looking for possible funding from ECRDA and DAFF | Financial Reports Bank Statements Receipts. | Head: Trading Enterprises
2.3 Utilise Adam Kok Farms as a primary production hub for agricultural produce | 2.3.1 Number of cattle produced, sourced and supplied to Umzikantu Abattoir. | P20 Adam Kok Livestock Sales | 2_2.3_2_P20 | - Purchase, condition (for a maximum of 100 days) and distribute cattle for Umzikantu Abattoir Breeding - Heifer Exchange Programme -Livestock Trade Fair - Cattle Branding |  |  | 960 Cattle produced, sourced and supplied to Umzikantu Abattoir | 190 cattle produced, sourced and supplied to Umzikantu Abattoir | 320 cattle produced, sourced and supplied to Umzikantu Abattoir | Partially achieved: 385 cattle produced, sourced and supplied to Umzikantu | Less 125 cattle. The supply was per the Abattoir demand | Targets will be revised from Quarter 3. | Cattle transfer reports. | Head: Trading Enterprises
| 2.3.2 Revenue generated from cattle produced and sold to other markets | [5 empty] | R1,375 000.00 generated from cattle produced and sold to other markets | No target | No target | R2 280 400.30 generated from cattle produced and sold to other markets | We had no plan to sell this period but due to favourable prices we decide to sell | Not applicable | Cattle sales invoices/receipts
| 2.3.3. Number of hectares utilised for animal feed |  | 2_2.3_3_P21 | #VALUE! |  | 46 ha utilised for animal feed | 60 ha utilised for animal feed (40 ha maize grain and 20 Ha winter pastures) | Procurement of inputs | Land preparation and planting | Achieved | Not applicable | Not applicable | . Requisition Vouchers (procurement of inputs) . Tractor log books . GPS coordinates . Pictures
| 2.3.4 Number of hectares utilised for crop production |  |  |  |  | 11.3 Ha utilised for crop production | 11.5 ha utilised for crop production ( 8 ha cabbage and 3,5ha butternut) | Procurement of inputs Land preparation and planting for cabbage | Land preparation and planting of cabbage and butternt Harvesting of cabbage | Achieved | Not applicable | Not applicable | . Requisition Vouchers (procurement of inputs) . Tractor log books . GPS coordinates . Pictures
| 2.3.4.1 Revenue generated from sale of crops | [5 empty] | Generate R1 403 213.00 from crop sales | No target | R155 714.13 generated from cabbage sales | Partially achieved: R144 700.06 generated for crop sales. | Partially Achieved: Only R36 130.48 generated from this year's crop due to the following reasons: There is too much cabbage in the market during this period. The hghest contributing factor is the Covid 19 relief support which has been afforded small holder farmers for production. There was also generally few events that would lead to higher buying. | Need for high level of observation of production trends during such periods | Sales invoices/ receipts
STRATEGIC GOAL 3 | Diversified Partnerships that Promote Inclusive Socio-economic Development and Growth.
Strategic Objectives | Key Performance Indicator | Project Names | Indicator Code | Interventions | 2017/2018 Budget | Baseline 2019/20 | 2020/2021 Annual Performance Target | Quarter 1 | Quarter 2 | Midterm Actual Perfomance | Perfomance Variance & Reasons | Corrective Measure | Means of Verification | Custodian
[8 empty] | (01 July 2020 - 30 September 2020) | (01 October 2020 - 31 December 2020)
3.1 Optimize linkages of meat industry value chain that enhance functionality of Umzikantu Abattoir by 30 June 2020. | 3.1.1 Number of signed and implemented partnership agreements that enhance functionality of Umzikantu Abattoir | P25 Abattoir Strategic Partnerships | 2_3.1_1_P25 | - Establish and maintain partnerships with livestock (cattle, sheep and pigs) producers, marketers and/or speculators. - Facilitate off-take agreements with wholesalers and public entities like Correctional Services, Hospitals, etc. - Facilitate off-take agreements for hides and skins. - Establish partnerships with meat hawkers for sale of offal, feet and heads. |  |  | 1 new partnership agreement that enhance functionality of Umzikantu Abattoir signed and implemented | 2 meetings set for the preparation of the | 1 Partnership agreement that enhance functionality of Umzikantu Abattoir signed and Implemented | Achieved: One Meeting Held | One Meeting Held at the abattoir with One potential Partner | Not applicable | * Minutes and Attendance Register (Q1+ Q2). * Signed Partnership Agreement.(Q3). * Implementation progress report.(Q4) | Head: Trading Enterprises
| 3.1.2 Number of signed and implemented off-take agreements for sale of meat from Umzikantu Abattoir. | [5 empty] | 5 Off-take agreement for sale of meat from Umzikantu Abattoir signed and implemented. | 3 Meetings in facilitation of the offtake agreement | 3 Off-take agreement for sale of meat from Umzikantu Abattoir signed and implemented. | Partially Achieved: One Offtake Agreement signed. | 2 Off take agreements not signed. This was because most of the business owners were busy during this period | All these will be done during the third and fourth quarter | * Attendance Register & Minutes (Q1 = Q2). * Signed Off-take Agreement (Q3+Q4) | Head: Trading Enterprises
3.2 Optimize linkages of fruit and vegetable industry value chain in support of Kei Fresh Produce Market by 30 June 2020. | 3.2.1 Number of signed and implemented partneships agreements that enhance functionality of Kei Fresh Produce Market. | P26 Fresh Produce Market Strategic Partnerships | 2_3.2_2_P26 | - Develop and maintain partnerships with Local Municipalities to assist local farmers to produce and supply the KFPM. - Facilitate involvement of local PDI’s in the Market Agency business. |  | 1 Partnership agreement | 1 new partnership agreement signed with local non-commercial farmer to supply KFPM with agricultural produce. | No target set for this quarter | No target set for this quarter | No target set for this quarter | No target set for this quarter | No target set for this quarter | 1 Partnership Agreement Signed. | Head: Trading Enterprises
| 3.2.2 Number of signed and implemented off-take agreements with local non-commercial farmers to supply KFPM with agricultural produce. |  |  |  |  | 2 Off-take agreements. | 2 new off-take agreements signed and implemented with local non-commercial farmers to supply KFPM with agricultural produce. | 1 new Off-take agreement signed and implemented with local non-commercial farmers to supply KFPM with agricultural produce | 1 new Off-take agreement signed and implemented with local non-commercial farmers to supply KFPM with agricultural produce | Achieved: Two (2) new Off-take agreements signed with local non-commercial farmers to supply KFPM with agricultural produce. | None | None | * Attendance Register, Minutes (Q1+ Q2) * Two Signed Off-take agreements.(Q3) | Head: Trading Enterprises
3.3 Mobilise resources for strategic economic infrastructure initiatives through the establishment of strategic partnerships | 3.3.1 Rand value of resources mobilised through strategic partnerships | Resource Mobilisation |  | Establish value-adding partnerships that will result in additional resources being mobilised with public and private sector institutions |  | New target | R10 million | No target set for this quarter | A resource mobilisation plan is developed. | Partially Achieved: first step in a sequence of incremental steps done with identification of funding opportunities for purposes of alignment with Ntinga priorities based on company mandate and strategy | Review of identified funding opportunities and actual development of resource mobilisation business plan. | internal review of identified opportuinities and appointment of service providers to develop the resource mobilisation plan. | Copy of resource mobilisation plan, progress report on resource mobilisation | Chief Executive Officer
3.4 Develop, Support and promote SMMEs as a catalyst for economic development and growth and innovation by 30 June 2021. | 3.4.1Development of Trade and Investment Plan | Investment Promotion and Facilitation |  | Development of Investment Plan |  | Trade and investment brochure | Investment Plan Developed and Implemented | No target set for this quarter | An Investment Promotion and Facilitation Plan is developed | Partially Achieved:: draft investment plan concept document developed. for internal and external stakeholders. | Planned internal and external stakeholder consultative meetings could not sit due to time and covid -19 constratints. | Virtual internal and external consulative meetings scheduled for 3rd quarter 2020. | Copy of Investment Promotion and Facilitation Plan, progress report on Investment Promotion and facilitation | Chief Executive Officer
| 3.4.2 number of new Domestic Investors attracted into O.R. Tambo region | Investment Promotion and Facilitation |  | Market the district as an investment destination |  |  | 1 New Domestic investor attracted into O.R. Tambo region | No target set for this quarter | A Domestic investment Promotion and Facilitation Plan is developed | Partially Achieved: Investment through RAFI Beef being attracted to the dsitrict in Ingquza Hill and Adam Kok Farms to a collective number of 2000 livestock improvement cattle valued more than R30 000.00. | Complete fencing and launch project in respect of Lambasi Beef Site, finalise lease agreement and fencinmg in resepct of Hlabathi Beef site and finalise consultation with Ntinga BOD in respect of use of Adam Kok Farms (Llwelin Farm) for the beef programme. | Finalise land lease with Mkambati Land Trust in respect of the Hlabathi Beef site, submit proposals to Ntinga BOD in the 3rd Quarter in respect of the Adam Kok Farms. | Copy of Investment Promotion and Facilitation Plan, progress report on Investment Promotion and facilitation | Chief Executive Officer
| 3.4.3 number of business incubators piloted | Business incubation |  | Establish agriculture business incubator |  | New target | 1 Business incubator established | No target set for this quarter | A proposal on a business incubator is developed | Partially achieved: Establishment of the RAFI-Tsori Capital partnership for the planning and implementaion of the RAFI Fresh Produce Programme and identification and visit to sites earmarked for fresh produce withij the district municipality. | Development of business and resource mobilisation plans. | Maintanance of momenntum on commenced implememtaion processes. | Copy of proposal on business incubator | Chief Executive Officer
STRATEGIC GOAL 4 | Dynamic, Capable and Sustainable State Owned Company.
Strategic Objectives | Key Performance Indicator | Project Names | Indicator Code | Interventions | 2017/2018 Budget | Baseline 2019/20 | 2020/21 Annual Performance Target | Quarter 1 | Quarter 2 | Midterm Actual Performance | Performance Variance & Reasosn | Corrective Measure | Means of Verification | Custodian
[8 empty] | (01 July 2020 - 30 September 2020) | (01 October 2020 - 31 December 2020)
4.1 Ensure Business Processes, Tools and Systems that support implementation of the Strategy and continued viability of the organisation by 30 June 2021 | 4.1.1 Sound Financial Management and Accurate reporting | P30 Financial Management, Systems and Reforms | 3_4.1_1_P30 | - Financial management and reporting. - Supply Chain Management reforms and Oversight. - Asset Management. |  | Final Annual Budget approved by 30 May. | Final Annual Budget approved by 30 May. | No target set for this quarter | No target set for this quarter | No target set for this quarter | Not applicable | Not applicable | *Board resolution and *Proof of submission to parent municipality | Chief Financial Officer
[6 empty] | MFMA S87(11) monthly finance reports prepared within 7 working days after the end of the month. | MFMA S87(11) monthly finance reports prepared within 7 working days after the end of the month. | Monthly budget reports submitted to the parent municipality within 7 working days after the end of every month. | Monthly budget reports submitted to the parent municipality within 7 working days after the end of every month. | Achieved: Monthly budget reports submitted to the parent municipality within 7 working days after the end of every month. | None | Not applicable | * Proof of submission to parent municipality | Chief Financial Officer
[6 empty] | Quarterly finance reports prepared and submitted to the Board within 30 days after the end of the quarter. | Quarterly finance reports prepared and submitted to the Board within 30 days after the end of the quarter. | 2019/2020 fourth quarter finance report prepared and submitted to the Board within 30 days after the end of the quarter. | 2020/2021 first quarter finance report prepared and submitted to the Board within 30 days after the end of the quarter. | Achieved: 2019/2020 fourth quarter and 2020/2021 first quarter finance reports prepared and submitted to the Board within 30 days after the end of the quarter. | Owing to disruptions due to COVID-19 compliance timeframes were extended by two months. Actual date of submitting to the Board the 2019/2020 fourth quarter finance report was 28 August 2020. | Not applicable | * Quarterly Fiinance Reports. * Minutes of Board Meetings. | Chief Financial Officer
|  |  |  | Board of Directors adopted Mid-year budget & performance assessment report with recommendations |  | Mid-year budget & performance assessment report submitted to Board of Directors and Parent Municipality by 20 January. | 2020/2021 Mid-year budget & performance assessment report submitted to Board of Directors and Parent Municipality by 20 January 2021. | No target set for this quarter | No target set for this quarter | No target set for this quarter | None | Not applicable | *Mid-year assessment report. * Proof of Submittion to the Board and to the Parent Municipality. | Chief Financial Officer
|  |  |  | - Review of finance related policies and standard operating procedures (SOP). - Clean administration. - Audit of Annual Financial Statements. - Responding to A-G Queries. - Turnaround strategy to resolve audit queries. |  | Audit Action Plan to resolve audit queries developed | Audit Action Plan to resolve audit queries developed | No target set for this quarter | Audit Action Plan to resolve audit queries developed | Not applicable. Date of issuing the 2019/20 audit report which is the basis for development of the audit action plan has changed to end February 2021. | None | SDBIP to be revised so that this target is moved to the third quarter of the 202/21 financial year. | *Audit Action Plan * Audit Action Plan Implementation Report | Chief Financial Officer
[6 empty] | Obtain unqualified audit report from Auditor General | Obtain unqualified audit report from Auditor General | No target set for this quarter | Obtain unqualified audit report from Auditor General. | Not applicable. Date of issuing the 2019/20 audit report has changed to end February 2021. | None | SDBIP to be revised so that this target is moved to the third quarter of the 202/21 financial year. | Audit Report | Chief Financial Officer
| 4.1.2 Rand value of investment income collected. |  |  | 100% collection of budgeted revenue. |  | R650 000 investment income collected. | R450 000 investment income collected. | R105 000 investment income collected. | R115 000 investment income collected. | Partially Achieved: R131 793 investment income collected. | R88 207 of the projected investment income could not be collected due to the reason that revenue collection targets were not met. Investment income is dependent on revenue collection from other sources. | Improve revenue collection by implementing corrective measures outlined under Goals 1 and 2 above. | Investment register | Chief Financial Officer
| 4.1.3 Annual Financial Statements submitted to Audito General by 31 August |  |  | - Preparation of credible ledger accounts up to Statement of Financial Position. - Submission of Annual Financial Statements to the Audit and Risk Committee & Auditor General |  | Annual Financial Statements prepared by 31 August. | 2019/2020 Annual Financial Statements prepared by 31 October 2020. | No target set | 2019/2020 Annual Financial Statements submitted to Auditor General by 31 October 2020. | Achieved: 2019/2020 Annual Financial Statements submitted to Auditor General by 31 October 2020. | None | Not applicable | * Signed AFS * Proof of Submission. | Chief Financial Officer
| 4.1.4 % of suppliers paid within 30 days from date of invoice |  |  | Reconciliation of creditors with supplier statements & processing of journals |  | 100% of suppliers paid within 30 days from date of invoice | 100% of suppliers paid within 30 days from date of invoice | 100% of suppliers paid within 30 days from date of invoice. | 100% of suppliers paid within 30 days from date of invoice. | Achieved: 100% of suppliers paid within 30 days from date of invoice. | None | Not applicable | Supplier payment vouchers. | Chief Financial Officer
| 4.1.4 %Procurement Done with local suppliers |  |  | Compile Annual Procurement Plan and SCM Report |  | 50% value of the procurement done with local suppliers | 50% value of the procurement done with local suppliers | No target set. | No target set. | No target set for this quarter | None | Not applicable | Annual procurement plan. | Chief Financial Officer
[8 empty] | 50% of Procurement done with local suppliers | 50% of Procurement done with local suppliers | Achieved: 50% of Procurement done with local suppliers | None | Not applicable | SCM Paragraph 6 reports. | Chief Financial Officer
| 4. 1.5 Annual Review of the Strategic Plan | P32 Corporate Governance | 4_4.1_2_P33 | Review Strategic Goals and Objectives Risk Management review Register/ top ten strategic risks |  | Annual review of strategic plan by 30 April. | Annual review of strategic plan by 30 April. | No target | No target | No target set for this quarter | None |  | Signed reviewed Strategy | Chief Executive Officer
| 4.1.6 Number of compliance reports submitted to the Board, ORTDM and Auditor General | P33 Legal Compliance | 4_4.1_2_P33 | - Number of performance reports submited to the relevant stakeholders |  | 4 Quarterly performance reports; 1 Midterm performance report; 1 Annual Performance report, and 1 Annual Report submitted to the Board ,Parent Municipality and AGSA | 4 Quarterly performance reports; 1 Midterm performance report; 1 Annual Performance report, and 1 Annual Report submitted to the Board ,Parent Municipality and AGSA | *2019/2020 4th Quarter Perfomance Report submitted to Board of Directors and Parent Municipality. | 2020/2021 First Quarter Perfomance Report submitted to Board of Directors and Parent Municipality | Achieved: 4th Quarter Perfomance Report and 2020/2021 First Quarter Perfomance reports were submitted to Board of Directors and to the Parent Municipality. | None | Not Applicable | * Proof of Submission to the Board, Parent Municipality and to AGSA. * Perfomance Reports: Q1- 4th Quarter Perfomance Report Q2- 1st Quarter Report Q3- 2nd Quarter Report - Midterm Report Q4- 3rd Quarter report * Board Minutes | Chief Executive Officer
[8 empty] | No target set for this quarter | *2019/2020 Draft Annual Perfomance Report submitted to Board of Directors, AGSA and to the Parent Municipality by 31 October 2020. | Achieved: 2019/2020 Draft Annual Report was submitted to the Board of Directors, AGSA and to the Parent Municipality | None | Not Applicable | * Proof of Submission to the Board, Parent Municipality and to AGSA. * Perfomance Reports: Q2- Annual Perfomance Report Q3- Annual Report * Board Minutes | Chief Executive Officer
| 4.1.7 Implementation of Perfomance Management Systems, monitoring and evaluation | P32 Corporate Governance | 4_4.1_2_P33 | Number Monthly Senior Management |  | 12 Monthly Senior Management meetings | 12 Monthly Senior Management meetings | 3 Monthly Senior Management Meetings | 3 Monthly Senior Management Meetings | Partially Achieved: 5 Meetings were held for the period under review | One meeting was not held in the first quarter due to difficulties experienced in connecting virtual | Not Applicable | * Attendance registers, * Signed Minutes. | Chief Executive Officer
| 4.1.8 Number of Board and Board Committee Meetings attended | P32 Corporate Governance | 4_4.1_2_P33 | -Number of Board meetings - Number of ARC meetings - Number of HRRC meetings - Number of SDIC meetings - Ntinga Annual General Meeting |  | 5 Board meetings 6 ARC Meetings 1 AGM 3 HRRC Meetings 4 SDIC Meetings 1 Exco Meeting | 5 Board Meetings | 1 Board Meeting | 1 Board Meeting | Over Achieved 7 Board meetings were held for the period under review. | Special Board meetings were convened at the request of the Board to attend to a specific matter. | Not applicable | * Attendance Registers * Draft Minutes * Agenda of the meeting * Meeting pack | Company Secretary
[7 empty] | 5 ARC Meetings 1 AGM 4 HRRC Meetings 4 SDIC Meetings 2 SEC Meetings | 1 ARC Meeting 1 HRRC Meeting 1 SDIC Meeting | 1 ARC Meeting 1 HRRC Meeting 1 SDIC Meeting 1 SEC Meeting | Achieved 2 ARC meetings were held for the period under review. 2 HRRC meetings were held. 2 SDIC meetings were held. 1 SEC meeting was held for the period under review. | Not applicable | Not applicable | * Attendance Registers * Draft Minutes * Agenda of the meeting * Meeting pack | Company Secretary
STRATEGIC GOAL 4 | Dynamic, Capable and Sustainable State Owned Company.
Strategic Objectives | Key Performance Indicator | Project Names | Indicator Code | Interventions | 2017/2018 Budget | Baseline 2019/20 | 2020/21 Annual Performance Target | Quarter 1 | Quarter 2 | Midterm Actual Perfomance | Performance Variance & Reasons | Corrective Measure | Means of Verification | Custodian
[8 empty] | (01 July 2020 - 30 September 2020) | (01 October 2020 - 31 December 2020)
4.2 Ensure functional excellence in the organisation | 4.2.1 Number of policies and SOPs reviewed | Review of policies and SOP |  | - Employee development - Leadership development - Inculcate a culture of compliance - Promote functional discipline - Recognise good performance - Critical vacant posts filled. |  | 15 policies reviewed. | 40 policies reviewed. | Review 10 PolicIes | Review 10 Policies | Over Achieved: 31 Policies reviewed | Policy review in the first quarter was conducted over 2 days instead of the originally planned 1 day thus covering many policies. | None | Reviewed policies. Board Resolution . Poilicy Handbook | Head: Corporate Services
| 4.2.5 Number of budgeted vacant posts filled | Filling of Critical funded posts |  |  |  | 128 Posts Filled | 9 budgeted vacant posts filled | 2 budgeted vacant posts filled | 7 budgeted vacant post filled | Partially Achieved: 2 budgeted vacant posts filled | The new positions were for the Meat Market which was estimated to be operational by December, but to date the construction has not yet commenced | The posts will be advertised after the commencement of Meat Market construction | Appointment Letters | Head: Corporate Services
| Number leadership development programmes completed. |  |  |  |  | New indicator | 2 Senior Managers enrolled on the leadership development programme | No target set for the period. | 2 Senior Managers enrolled on the leadership development programme | Partially Achieved: The candidates have submitted applications, still waiting for response | The closing date for applications is 5 March 2021 and the course will commense in March 2021 | The two Managers will enrol by the 5th of March 20221 | Enrolment certificates | Head: Corporate Services
| Number of staff development trainings implemented. |  |  |  |  | New indicator | …staff trainings conducted. | No target set for the period. | No target set for the period. | 1 Training Conducted | No target set for the period. | No target set for the period. | Training certificates | Head: Corporate Services
| Percentage of staff performance appraisals conducted. |  |  |  |  | New indicator | 100% of staff performance appraisals conducted. |  | 100% of staff performance appraisals conducted. | Partially Achieved: 1.57%of staff Performance Appraisals conducted | Performance Appraisals have been conducted to 2 Senior Managers. Performance agreements have not been signed by all employees | performance appraisals will be conducted to senior and middle management in the next quarter | Appraisal reports | All Senior Managers
4.3 Continously improve internal and external reputation and image of the institution by 30 June 2021 | 4.3.1 Well known corporate brand | Communication, Public Relations and Marketing |  | Corporate Communication, Public Relations and Marketing Plan |  |  | Communication and marketing policy developed and approved | Develop draft Communication and Marketing Policy in line with the new Mandate and SOC. Submit to management for engagement | Submit for Board Approval draft Communication and Marketing Policy | Partially Achieved- Not yet approved by the board | Draft Communication and Marketing Policy was presented to SEC Board Committee for approval on the 14th October 2020. It will be recommended for final board approval in the next board meeting in January 2021 | The Policy will be recommended for approval in January 2021 | Board approved Commmunication and Marketing Policy Board Resolution | CEO
[7 empty] | Participated in 2 campaigns / events | No target for the quarter | Participate in 1 Campaign/event | Achieved- Participated in Mhlonto Farmers Union workshop on 20th November 2020 in Qumbu. | Not applicable | Not applicable | Post Campaign/Event Report and Pictures
[7 empty] | 4 Media Statements / notice issued | Issue 1 Media Statement/Notice | Issue 1 Media Statement/Notice | Over Achieved-4 media statements/notices have been issued | 2 more media statements/notices issued due to urgent demand | Not applicable | Media Statement/Notice issued
[7 empty] | 4 reports on website management compiled | Compile 1 report on website management | Compile 1 report on website management | Achieved-2 reports on website management have been compiled. | Not applicable | Not applicable | Signed report on website management
4.4 Operational resilience: ensure that your business processes are documented, business process must be aligned to your business by 30 June 2021 | Sound documented business processes and systems, ISO | SOP |  | Develop business process in all your business units |  | New indicator | Revised and reviewed business processes for the entity | No target set for the period. | KFPM SOP revised |  |  |  | SOPs Approved | Chief Executive Officer & Head: Trading Enterprises
| Aligned business processes to your business |  |  | Reconcile business processes to business mandate and strategy |  | new Indicator | Entity business processes aligned | No target set for the period. | KFPM BUSSINESS PROCESSES reviewed |  |  |  | Business processes that talks to business strategy | Chief Executive Officer & Head: Trading Enterprises
| Capable workforce with relevant business needs |  |  | Identify talent from within and recruit needed personnel that complement business strategy |  | new indicator | Revise Proposed business structure | No target set for the period. | Productivity increased by 25% |  |  |  | Recruitment process and business organogram Performance Measure | Chief Executive Officer and Corporate Services
4.5 Strategic effectiveness dynamic soc capability | 4.5.1 Strategy developed ,reviewed and developed and implemented | Strategy | Strategy Developed |  |  | new indicator | 2019/2020 strategy | No target set for the period. | No target |  |  |  | Approval by the board | Chief Executive Officer
| 4.5.2 Governance processes developed and reviewed | Governance | Review meetings |  |  | new indicator | 2019/2020 strategy | No target set for the period. | No target |  |  |  | Approval by the board | Chief Executive Officer
| 4.5.3 Governance structures aligned to mandate of Ntinga | Structure | Committee meetings |  |  | new indicator | 2019/2020 strategy | No target set for the period. | No target |  |  |  | Approval by the board | Chief Executive Officer
| 4.5.4Resolutions and decisions of the board recorded and implemented | Resolution and decisions | Resolutiins documented |  |  | new indicator | 2019/2020 strategy | No target set for the period. | Per board meeting |  |  |  | Approval by the board | Chief Executive Officer
| 4.5.5 Compliance requirements on strategy executed | Compliance | Compliiance requiremance met |  |  | new indicator | 2019/2020 strategy | No target set for the period. | No target |  |  |  | Approval by the board | Chief Executive Officer
| 4.5.6 Monitoring and evaluation of strategy execution | Monitoring and evaluation | Monitoring and evaluation report |  |  | new indicator | 2019/2020 strategy | No target set for the period. | No target |  |  |  | Approval by the board | Chief Executive Officer